## Phase I - All Bond Projects
BOND CONSTRUCTION PROJECTS
Project Name | Project Manager | Project Phase | Architect | Architect COI | General Contractor | P&P Bonds on $150K > Contractors Only | General Contractor COI | Forecasted Temp. Occupancy Cert. (TCO) Date | Estimated Completion | Construction Percent Complete | BOE Contract Approval | Schedule | Budget | TCO Real Date | General Updates / Major Issues Concerns | Legal Review | 11 Month Warranty Walk | 23 Month Warranty Walk
Broomfield Heights MS | Charles Zachemsky / Matt Johnson | 1 | TreanorHL PO 461989 | 2023-09-14 | JHL PO 462358 | Western Surety 30208788 | 2024-03-07 |  | 2024-08-01 |  | N/A |  |  |  | 7/24 SD estimate is over budget but we have a pathway to get to budget. CTE is a major overage; significant redesign is necessary. 7/31 parent email to principal concerned about brick wall at SE corner. Trying to get JHL to do exploratory demo and stabilization ASAP. 8/18: JHL demo revealed structural concerns under SE wall / ramp. Shoring company engaged by JHL to install temp shoring. 9/11 Shoring installed. DDs being priced by JHL. SE working on design to stabilize wall & outdoor deck. 10/27 Working on finalizing CDs. Should be within budget with addition of inflation funds. Structural design for retaining wall being dialed in with assumptions made as to condition of concrete wall behind the brick. ROM is $500K for now pending condition assessment once brick is down. 11/29 CDs issued and being priced up for GMP by JHL. Receiving revised cost for wall condition on 11/31 for CBOC request. 1/30/24 CBOC approved add'l $800K for wall problems. GMP approved by BOE. Follow Up DATA & staff meetings scheduled. 3/25 Buyout under way, mover walk this week, furniture vendor selected. 5/20 Still on track. Buyout complete. JHL starting 5/24 with some select prep work. 6/17 Structural eng. met on site Friday 6/14 to confirm state of wall. Looks good to proceed with soil nailing. Steel beam supporting entry canopy is very degraded. Engineer is confirming splice detail to repair. 7/1 On track. Soil nailing beginning today. Waiting on SE for final beam fix. Found roof drain needing help. 9/9 JHL took care of six figure smell and sewer repair (not caused by bond work). Work is backfilled and they are gearing up for final steps of wall reconstruction. PL items and honey-dos are ongoing. 9/30 Wall shotcrete & flatwork are wrapping up. Railings last to go. Minimal interior presence. 10/21 Flatwork is all that's left outside. A couple of interior change order items forthcoming. 12/2 Minor change order work finishing up. Steel railing outside field measured and ordered...should install over holiday break and open south entries. 1/6 Custom drain for upper deck shipped late and arrived week of new years. JHL team is expediting installation & pour back. Charles to check on options for library settling | 8/9: JHL Contract in Legal mid July. Contract signed and PO issued.
Broomfield HS | Charles Zachemsky / Matt Johnson | 1 | TreanorHL PO 461987 | 2023-09-14 | JHL PO 462357 | JHL Western Surety 30208787 --------------------- JKS Industries for Abatement American Alternative Insurance Corp #S7A2SU0002548 | 2024-03-07 |  | 2025-08-01 |  | 2023-05-09 |  |  |  | 9/11 DDs issued 9/8; being priced by JHL. School staff concerned about press box, add'l restroom location & field branding. 10/27 Finalizing CDs. Should be within budget with addition of inflation funds. 11/29 CDs issued and being priced up for GMP by JHL. 1/30/24 GMP approved by BOE. Follow Up DATA & staff meetings scheduled. 3/25 Buyout under way, mover walk this week, furniture vendor selected. Minor abatement this week. 5/20 Mover started today staging for weight room move. Continuing this week with moving prep at weight room & trades/CAD classrooms. Auditorium sub also starting this week. 6/17 First phase of abatement a couple days ahead. JHL scope on track with interior and exterior work. Working with JKS to add weight room abatement this summer...disconnect between JHL & JKS. 7/1 Still on track. Abatement progressing w/ weight room. Had 'major fiber release' last week; all taken care of. 9/9 Week of 9/9-9/13 is big week to install/move a lot of FFE back in to turn over building trades set of rooms for use starting 9/16. Choir room ongoing for turnover first week of October. 9/30 Last of building trades area turned over 9/26. Choir move in scheduled for 8/14. Planning for early abatement over breaks to get ahead of summer '25. Stadium restroom building ongoing. January turnover. 10/21 Choir moved to new room on 10/14. Making preparations with Anser, JHL and JKS to get abatement work going over holiday & spring breaks to get ahead of summer '25. 12/2 Abatement work over Thanksgiving break went fine. JHL doing 'clean' demo up to holiday break and more abatement work. 1/6 Holiday break abatement work went as planned. JHL proceeding with restroom building with planned turnover in March. | 8/9: JHL Contract in Legal mid July. Contract signed and PO issued.
Early Connections @ ARHS | Charles Zachemsky | 1 |  |  | Fry & Associates PO#461577 | West Bend Mutual #2536947 | 2023-02-21 | [7 empty] | 10/27 Shade shelter is only thing not complete but program is using the new playground. Thanksgiving break planned for shelter installation. 11/29 Shelter complete and inspected. Vendor will return in spring to top dress & overseed laydown area.
Fireside ES | Charles Zachemsky | 1 | TreanorHL PO 461988 | 2023-09-14 | JHL PO 462359 | Western Surety 30208789 | 2024-03-07 |  | 2024-08-01 |  | N/A |  |  |  | 7/24 SD estimate is close to budget. 9/11 DDs being priced. No issues with design. 10/27 CDs complete. Resolved differences between transportation & school staff. Should be in budget with addition of inflation funds. 11/29 CDs issued and being priced up for GMP by JHL. 1/30/24 GMP approved by BOE. Follow Up DATA & staff meetings scheduled. 3/25 Buyout under way. On rails. 5/20 Still on track. Buyout complete. JHL starting 5/24 with some select prep work. 6/17 Had ROW issue upon starting parking lot work. Worked it out with Louisville and only lost 2 days. JHL is catching up and is back on track. Rest of work is on rails. 7/1 ROW permit in hand. All is on track. 9/9 All is fine at FES. A few late order items installing in the next week or two. A few honey do items. 9/30 Last couple interior items waiting on materials is complete. Working towards closeout. 12/2 Barn door add was completed over Thanksgiving break. Getting second quote for Valcom system. 1/6 Cafe/stage stair treads re-installed over holiday break. Restroom floor drain was discovered to be clogged with grout; JHL working on clearing it. | 8/9: JHL Contract in Legal mid July. Contract signed and PO issued.
Monarch Campus Boilers | Charles Zachemsky | 1 | ~ | ~ | Design Mechanical PO 460623 | Fidelity & Deposit #9404331 | [8 empty] | 7/18-Rainy June & into July caused delayed start. Locates & potholing complete. Many utilities in the way so excavation will be slow. DMI still confident that they'll get cooling online by start of school. Heating system flush will take a couple of weeks so there will be a presence at both schools at the start of the school year. 7/31-A 6" irrigation line slip joint came loose last week and flooded the trench. Delayed setting pipe in the ground until this week. 9/11 Hot water circuit close to completion of cleaning and re-introducing glycol. Iconergy performing retro-commissioning 9/12 Glycol will be pumped into the system on 9/25 as it's a non-student day. DMI will have personnel watching for leaks throughout both schools while glycol is being introduced. 10/27 Glycol on hot side complete. Commissioning ongoing but all good with hot side. Cold side glycol planned for 11/10. New pot feeders & glycol feeders to be installed as soon as they arrive (will not impact operation of the system). 12/6 - DMI supposed to install exhaust fan on AHU-4 over break. Follow-up meeting needs to be scheduled 3/25 Iconergy contracted for C-wing airflow design for Phipps to do work in conjunction with bond scope. DMI POOL being closed and $ transferred out. 5/20 Glycol work done per quantities provided to DMI. Will get O&Ms, sign off by Iconergy, advertise and closeout. 7/1 No response yet on request for remaining O&M materials. Only got boilers; nothing on pumps, feeders, piping, etc. 9/9 Received all closeout items and will advertise.
Monarch C-wing | Charles Zachemsky | 1 | Iconergy | ~ | [10 empty] | Iconergy is developing a design to fix issues which will be incorporated into the overall design for GH Phipps to perform with bond scope. 7/1 Iconergy is finalizing design for inclusion in DD set. 9/9 Design is to RTA for inclusion with project
Modular Factory | Charles Zachemsky | 1 | ~ | ~ | Building By Design | Bonds Not Required (not tracking funding) | 2023-02-08 | [7 empty] | 7/18-Lawsuits pending. 7/24 Neighbors filed an injunction to stop work. Failed after hearing on 7/28. 7/31 - Groundbreaking scheduled for 8/14 ish. 9/11 Earthwork ongoing. Neighbor complaints are going to CoB so unsure of issues. 9/12 Caisson drilling to begin 9/25. Metal building delivery scheduled for 10/4-11. The 14 trailers of materials will be laid down in large native area between greenhouse and building site. 10/27 Piers completed a week early. Steel building is on site. Sanitary sewer starting week of 10/30. Working on solution to keep culinary deliveries uninterrupted. 1/30/24 Foundations complete. Steel structure going up. Electricity tie in is last utility to be completed. 3/25 Structure complete. Skin in progress. Indoor slab in progress. 5/20 Skin 75% complete, roof complete, slab ~40% complete. 7/1 Skin & roofing complete. Interior framing complete. MEP in progress. Disconnect in design with extents of asphalt but working it out. 9/9 Finishing project and getting ready for ribbon cutting on 10/23 @ 4pm 9/30 Last hurdle is Xcel energizing transformer. Some coordination with IT ongoing.
Lafayette Bus Terminal | Gene Temanson | 1 | ~ | ~ | TBD | Bonds Not Required | TBD | 2024-07-31 | TBD | 99% | NA |  |  |  | 10.21 - Units are operational and WiFi seems to be functioning 11.04 - Units are operational and WiFi seems to be functioning
Boulder Bus Terminal | Gene Temanson | 1 | ~ | ~ | TBD | Bonds Not Required | TBD | TBD | TBD |  | NA |  |  |  | 11.04 - Anticipate drawings in late November. 11.18 - Drawings recieved and review scheduled for 11.19 12.02 - BVSD and Xcel reviewed drawings. Still waiting on estimated cost of work from IMEG.
Nederland ES ADA Restrooms | Gene Temanson | 1 | RTA PO 461279 |  | JOC Construction PO 461919 - B | Westfield Ins 310482X |  | 2023-07-20 | 2023-07-30 | 100% | NA |  |  |  | 12-11 - TCO received. Third attempt at partition hinges was unsuccessful. JOC has ordered replacements with delivery scheduled for (approximately) 12-15 01-22 Work complete and verified. Working on documentation to legal
New Vista HS | Gene Temanson | 1 | MOA PO 461763 & PO 460508 | 2023-08-29 | A&P PO 461704 | Continental Insurance Co #30201156/47-SUR-300007-01-0407 |  | 2024-12-12 | 2025-07-30 | 75% | 2023-08-22 |  | City of Boulder Use Tax impact - $800,000 |  | 11.04 - Finishes continue. IT Hub relocated. TCO date mid Dec. 11.18 - Finishes continue. TCO date mid Dec. 12.02 - Finishes continue. Punch scheduled to start next week. TCO date remains mid Dec.
University Hills ES | Gene Temanson | 1 | BVH Architects PO 462111 | 2023-06-02 | Taylor Kohrs PO 462307 | Western Surety 30208810 | 2023-06-02 | 2024-07-30 | 2024-07-30 | 99% | 2023-12-12 |  |  |  | 11.04 - Working with TK on closeout. 11.18 - Final CO executed for final contract amount. Advertising continues. Due to delays caused by TK and eB, I don't expect closeout going to the board in Dec. 12.02 - Still waiting on TK for final billing and closeout. | 8/9: Taylor Kohrs Contract in Legal 7/26/23.
Lafayette ES Heating Pumps | Gene Temanson | 1 | Cator Ruma PO 461703 & PO 463024 |  | TBD | Bonds Not Required | TBD | TBD | TBD | 99% | NA |  |  |  | 10.21 - Work complete and functioning but working off last punchlist/Cx items. 11-.04 - Work complete and functioning but working off last punchlist/Cx items.
Halcyon Radon Mitigation | Gene Temanson | 1 | NA | NA | TBD | TBD | TBD | TBD | TBD | 100% | NA |  |  |  | 02.22 - Testing is now scheduled for the end of February/beginning of March 03.18 - Test results were fine. Roger and Carey want to do another round of testing (date TBD). 04.29 - Waiting on new test results
HVAC Controls | Maint - Travis Cook | 1 | ~ | ~ | Westover PO# 30 POs | [6 empty] | Ongoing
Alicia Sanchez ES | Stephen Henry | 1 | Wold Architects PO 462082 | 2023-08-30 | Alliance Construction PO 462397 | Western Surety 30198616 |  |  | 2024-08-01 | 95% | 2024-01-23 |  |  |  | 10/21/2024 - Final pieces (Shade structure and last two table to go in over Thanksgiving break - anticipating advertising in December for BOE agenda in January 01/06/2025 - Project complete - Pending final billing and reconciliation from Alliance to closeout | 8/9: Alliance Contract in Legal 8/8/23.
Boulder Prep | Stephen Henry | 1 | BVH Architects PO 462144 | 2023-06-02 | Taylor Kohrs PO 462350 | Western Surety 30208811 | 2023-06-02 |  | 2024-08-01 | 95% | 2024-01-23 |  |  |  | 01/03/2025 - Storefront doors are being installed as of today to be completed by next week. | 8/9: Taylor Kohrs Contract in Legal 7/26/23.
Columbine ES | Stephen Henry | 1 | BVH Architects PO 462110 | 2023-06-02 | Taylor Kohrs PO 462351 | Western Surety 30208809 | 2023-06-02 |  | 2024-08-01 | 100% | 2024-01-12 |  |  |  | 10/21/2024 - Working through final CO's and closeout docs with TK - looking to advertise in November for BOE agenda in December 01/06/2025 - Final billing submitted - Planning to have in the January 28th BOE meeting for final closeout. • School is requesting funding to make repairs or replace the Marquee out front | 8/9: Taylor Kohrs Contract in Legal 7/26/23.
Ed Center Rooftop Units | Stephen Henry | 1 | Eidos PO 462345 |  | TBD (End of May DD Set will determine direction) |  |  |  | TBD | 0% |  | TBD | Cost Estimate is trending ~570k over budget |  | 9/30/2024 - Moving forward with MW Golden as CMGC and meeting with them today. 10/21/2024 - Expecting pricing for review later this week 10/31/2024 - Budget came in at 771k for the base CMGC scope including AAON units.
Lafayette ES | Stephen Henry | 1 | Wold Architects PO 462113-B | 2023-08-30 | Alliance Construction PO 462396 | Western Surety 30198617 |  |  | 2024-08-01 | 100% | 2024-01-23 |  |  |  | 8/12/2024 - All work is complete. 10/21/2024 - Targeting final advertising in November for BOE Agenda in December 01/06/2025 - Complete | 8/9: Alliance Contract in Legal 8/8/23.
Shade Shelters (4 schools) - COMPLETE Meadowlark Emerald Halcyon Douglass | Stephen Henry | 1 | BVSD | ~ | A to Z Recreation PO 461830 | Not Required |  |  | 2023-10-25 | 100% | N/A | Meadowlark - Complete Emerald - Structure complete the week of 11/6 * Modifications to the conc. completed week of 11/27 Halcyon - Completed the week of 11/13/2023 Douglass - Completed the week of 11/27 |  |  | 9/30/2024 - All structures are signed off and complete.
Roofing Projects (4) Aspen Creek (2023) Eldorado (2023) Lafayette Elementary (2024) Louisville Middle (2025) | Stephen Henry | 1 | RoofTech PO 461912 |  | Eldo - Superior Roofing Aspen - Superior Roofing Lafayette ES - B&M Roofing Louisville Middle - TBD | Travelers Eldo #107794291 AC #107817931 B&M Western Surety Laf #30215453 | B&M COI 2024.03.28 |  | 2024-08-01 | Aspen Creek ~ 100% Eldorado PK8 ~ 99% Lafayette ES ~ 0% Louisville MS ~ 0% | 5/23/2023 5/23/2023 TBD TBD |  |  |  | 7/29/2024 - Louisville scheduled to go out for bid later this year for work next summer 9/9/2024 - The Louisville MS Scope will be put back into the overall bond project with Howell for them to manage directly.
Justice HS | Stephen Henry | 1 | Wold Architects PO 462114-B | 2023-08-30 | Alliance Construction PO 462395 | Western Surety 30198618 |  |  | 2024-08-01 | 100% | 2024-01-23 |  |  |  | 7/11/2024 - Work is complete including punch items. Tracking for the August 5th BOE meeting for closeout 10/21/2024 - Getting final pricing on irrigation modifications through Phil 10/31/2024 - Working on getting a second irrigation quote to proceed with modifications. | 8/9: Alliance Contract in Legal 8/8/23. - Complete
Angevine MS | Christoph Konradi | 1 | HordCoplanMacht PO 462091-B |  | A&P PO 462419-B | Continental Insurance Company 30215159 47-SUR-300007- 01-0419 |  |  | 2024-08-01 | 95% | 2023-05-09 |  |  |  | 02-03 - FGMP $2,779,976, TOTAL anticipated contract $2,872,035. 08-02-2024: On track for TCO week of August 5th. Already have permission for teachers to occupy from DFPC 08-05: Walking with Fire Marshall today, DFPC tomorrow 08-12: Received CO, There are some FFE issue with late delivery but we are working on it. Where do we get TVs??? 08-20: Job complete, TCO received. Need to repour ramp in cafeteria, HCM will cover cost. GC Contingency approximately $80k 08-26: Ramp at cafeteria needs some modifications. 09-09: Ramp planning on going, work is being scheduled. Exploring ceiling tile replacement. 09-16: Branding Graphic on going walking with kara on 9-18. Need Rulon quote for two control installs at Angevine. 11-04: Remaining items are graphic and ramp fix to be completed End of December. Ceiling tile will be assest in the remaining corridor. 01-06-2025: Ramped was redone looks good, Corridor ceiling at gym was redone, additional ceiling and walk off carpet is beeing tracked. | PO Written.
Centaurus HS | Christoph Konradi | 1 | HordCoplanMacht PO 462093-B |  | A&P PO 462418-B | CONTINENTAL 30201165/47-SUR-300007-01-0412 |  |  | 8/1/24 & 8-1-2025 | 65% | 2023-05-09 |  |  |  | 08-12: Received TCO, fire Hydrant work has started, There are some FFE issue with late delivery but we are working on it. Were do we get TVs??? 08-20: School opened on time. CTE scheduled for completion September 23. Remaining scope after summer of 2024: Press Box; RTU 17; Atrium windows; graphics; Shaw flooring replacement 1st floor. GC Contingency $446,597 plus some being held for specific items (Gym Roof $30K, Theater Curtains $2,636 08-26: Discussion on FFE delivery issues 08-26, CTE additon is on Track for 09-20, Tracking loose end on on the low voltage side, DHA draft received and was reviewed by IMEG will discuss with facillity on 8-26, 08-23 Discussion with Carlyn and Karl related to remaining scope for summer 2 and what will be done between now and next summer. 09-09: Working on some IT loose end, expecting a schedule that outlines feasibility of replacing the pressbox over christmas. CTE additiona tracking for 9-20 completion. Furniture installed the week of 09-23. Graphics for centaurus have to be in by November 13th this is a hot items GC is tracking. Add service will be approved for Jensen Hughes 09-09 after discussion with Arlie, Dillion, Carey, and Kris. 09-16: Need Rulon quote, for adjusted scope related to third classroom. Need Galaxy quote for Bells and speakers in teachers lounge 299A. Expecting clarification on CTE Fabrication shope trun over on 10-17. Classroom completion ETA is still 09-20. Jensen Hughes Manuals Draft is due October 1st. 09-30: Dustcollector duct work layout in the works was ordered friday 9-27, classrooms will be ready by 1st of november. Kitchen PR is discussed. Custodial space is in review, Travis is aware. 10-21: Dustcollector 95% complete, celebration for CTE is set for 25th, Seicne office Quote received ~37K, AP is finalising the polishing quote, Pressbox is set to begin work mid november. 11-04: Set back related to the dust collectore should eb resolved by friday 11-08. Pressbox construction is comencing 11-11. exploring pricing for a paltform. 11-18: Press Box is on hold pending decision on design changes, dustcollector on going, faculty was told to hold any dust producing activity in the space untill Jan 1st 2025, 12-02: Pressbox feed back has been collected, presentation to the Listening group will be scheduled time TBD, Panel work in the school has been completed over spring break, Shaw flooring did their last set of test, AP Woodshop work is on going. 01-06-2025: PressBox getting a fee for the redesign, tracking a courtyard design and nursing room, proceeding with the heating for custodial and cooling for the kitchen, Wood shop is in review by DFPC. | PO Written
Teaching Kitchen | Tom Blahak | 1 | Peter Hines PEH Architects PO 462539 | 2024-01-16 | JHL PO 462803 | Western Surety 30214688 | 2024-05-03 |  | 2024-09-27 | 100% 10-30-2024 |  |  | BOULDER TAX $23,171 |  | Original Job Budget $845,000. Construction budget $724,470 for equipment and GC. 12-26: 03-25-24: DD Estimate $1,740,887. OVER BUDGET by $994,954. 08-02: Setbacks: DOAS unnit delayed until September 16, trying to get it in by end of August: Electrical connections hit snafu, working on solution 8-12: New panel installed over the wekend, going forward with Option #2 08-20: Electrical problem solved, work is ongoing. DOES scheduled to ship 9-18. Curbs have been solved. Exhaust hoods are hung, Walk ins installed 9-8 DOAS unit and exhaust units to be installed 9-14-2024.Appliances are being set. Job progressing towards completion of 9-27 10-16: Working on Punch List. TAB ocurring 10-19, last step in permit sign off. OUTSTANDING: FF&E furnishings arriving 1st of November; Platform for DOAS Unit, collecting quotes; Additional doors requested by Carolyn, Thanksgiving break; HSS hook up of FOBS on additional doors 11-04: Need to follow up on Boulder tax, Door revision, maintenance platform. 11-18: Maintenance plateform walk will occure today11-18, updated warranty contact information, closeout document under review, record documentation is under way, 12-02: Cost for platfrom still out standing, Warrenty period has not started yet. 01-06-2025: received platform cost asked JHL to proceed with a full proposal. 01-13: Tom to get debriefing from Kris 01-28: CO #05 for the platform in E-Builder, Job Cost has been ammended to include additioinal $88,364 to cover the change order, rest will come from Contingency. Punch list as of 1-21: 1) Montague "Vectaire" ovens are still not working. 1 has been locked out because the door keeps closing creating a safety hazard to the students. JHL has put Great Lakes on notice to replace the 2 Montague ovens. Davis Carey is involved, new models are $7,500 each Factory rep came out, got 1 operational, reordered a new unit for the second one. 3) Seal on the freezer door needs to be redone. Heater on door frame needs to be verified that it is working. Great lakes working on. 2) The Volrath Induction plate needs 1 replacement convection unit. 4) The overhead door bent bottom panel still has not been replaced. Special Paint causes long lead of 12 - 14 weeks, expected end of February. 5) HSS install the FOBs in 2 new doors, 2-10: Change Order #005 done for platform, drawings forthcoming, 8 week lead time
Peak to Peak | Christoph Konradi | 1 | Treanor HL Architect PO 462753 |  | Fransen Pittman PO 462757 | Travelers Casualty 107959704 |  |  | 2025-07-15 | 19% of bond work | 2023-11-16 |  |  |  | 04-15: FP IGMP set to go to Board 04-23 Maximum Budget $12,251,655. E-Builder shows correct amount. 05:06: Phase 2 Permit obtained, comnstruction starts EOM. 05-20: State now wants 3 permits. Construction Starts June 3 06-03: Permits paid for, waiting for construction start. 6-10: Waiting for code comments, interior demo ongoing 6-26: Bid Pack #1 Demo issued, still have 5 permits pending. 7-29: Delivery problems with VAV's, Carpet, Doors, foundation pour for precast panels. 08-02: FP working through problems 8-12: Jobsite needs to ready for students 08-20: Foundation for precast ongoing. Problems with RTU not ordered. ROM is $207, anything over comes from contingency. Carpet arriving late for Middle School, Locker rooms will be unavailable for start of school, Pushing foundations for precast placement. $234k in contingencies, $416 with allowances. Precast panels scheduled for week of 8-26, late Bond Funds sit at 1,754,613 9-4: Job is slowly progressing 09-30: FP to finish contruction in March. 10-16: FP requesting Final Completion of base contract for April 3, 2025. No schedule yet for Critical Needs items. New CMU Wall in auditorium ROM $25,000 out of P2P Contingency 11-04: inperson meeting at Peak to Peak, walk site ETC... 11-18: Critical needs item for elevator mdernization is going to the board 11-19, time extension for their contract will need to go to the board in December, expecting a schedule on how criticals needs will be addressed, 12-02: extensions is inprocess to be approved, Elevator scope has been approved, 01-06-2025: They are making progress on their citical needs listes, there is a kone hickup, but jen is working on it.
Centennial Tennis Court | Matt Johnson | 1 | Farnsworth Group PO 462732 |  | Renner Sports Surface PO | Federal Insurance Company K41830414 |  |  |  | 90% |  |  |  |  | Demo ongoing, CO#1 pricing revision. 5/8/2024 - CO#1 is complete and executed by all parties. Demo is complete on the east courts and installing forms and reinforcing. Permitting is in plan review and "In process" as of this morning 5/14/24 - DFPC Permit Issued, BOD approved CO #1 5/15/24 - Renner provided updated schedule with completion date of 8-1-24 5/20/24 - Renner resumed onsite today, inspection tomorrow. 6/3/24 - All post tension courts placed, fillet schedule for next week 6/17/24 - ADA ramps placed, fencing fabric installation ongoing, fillet concrete placed. 7/1/24 - Renner to start surfacing 7-8-24, have requested plan to mitigate cotton issue, still have not been provided. 7/15/24 - Flood test completed, areas of concern identified and addressed. BVSD drafted a marked up plan for future refferecnce. Surfacing ongoing and making good progress. Farnsworth has not yet provided design for revised entry design. 7/29/24 - Surfacing placed, still waiting on fencing materials. Items still up in the air are the fencing extension, stair addition, and final grading / refresh of parking lot. Inspection has been scheduled for 7-30 @ 9am 8/12/24 - Renner completed sealants over the weekend, courts will be reopened today. Recived 2nd quote for apron concrete, and working on schedluing for this scope. BVSD / Renner are still in progress on the scheduling for the grading / native seeding. Fence extension 4-6 weeks after pricng is approved. 8/26/24 - Renner has provided pricng for fence extension, Certfied concrete issued PO for aporn concrete. Brouwn bros still hhave yet to corret their ada issue, and remove slabs. Pricing from Renner is far more then anticiated. I feel we should proceed via T&M, princing is not fair at this point. 9/9/24 - Apron placed, 2nd quote for fencing extension recived 4k savings (4 week leadtime from approval for installation). Renner has yet to provide smartbuy invoice for wing rework. Renner has also not provided pricing for landscape changes in scope. Due to recent pricing, we may need to go out for a 2nd quote. 9/16/24 - PO issued to metro fence for the fence extension, Renner has yet to complete punch list items. BVSD has made many requests to get pricing for the fginal grading & wing reowrk. Renner continues to not provide items in a timely manner. 9/30/24 - Brown Bros. onsite today to remove the out of compliance ramp section, and pads pplaced on unispected soils. Renner is onsite tody to revmove the sections @ the wings. BVSD noted that surfacing patching to take place over a weekend. Still waiting for occupency signange. 10/21/24 - Final grading complete, Renner still trying to complete sealant scope. Fence extension trageting end of this week. 11/4/24 - Renner working on warranty items, and close out. On 11.3.24 fence extension was completed by metro fence. 11/18/24 - Closeout still ongoing, sealant warranty item still open. 12/2/24 - Sealant was schedlued to be installed on 11.28 & 11.29. BVSD to confirm this has been completed. 1/6/25 - Sealant still not complete, ground is now montioring slab movement. Closeout for BOE has been reviewed & approved.
Fairview Tennis Court | Matt Johnson | 1 | Farnsworth Group PO 462733 |  | Renner Sports Surface PO | Federal Insurance Company K41830426 |  |  |  | 95% |  |  |  |  | Renner revising pricing, and format package for board review. 5/8/2024 - CO#01 has been submitted for board approval on the 14th of May Renner is asking for additional time after submission of the signed CO Permits are in plan review and "In process" as of this morning. 5/15/24 - DFPC permit issued, BVSD requested updated schedule relecting court completion early September, with all other activites completing shortly after. 5/17/24 - Renner provided updated schedlue refleting 9/6/24 complition date. Buillt own schedlue for tracking. 6/3/24 - Security fence installed, Renner sub Brightview demo has started. Should have larger equipment onsite today 6/17/24 - Demo complete, Brightview started removal of roadbase. Scope change to utilize on site roadbase forthcoming deductive CO. 7/1/24 - Soil prep 95% complete, days gained in schedlue. Working on Renner to start forming sooner. 7/15/24 - Forming work 90% complete, vapor barrier & reinforcing placed on first 4 courts. Renner notifed BVSD today that they are plainning for no slab pours this week due to finsh crews. This delay is crew avaibility and not due to project conditions. Change to black coated vinyl fencing could impact the overall completion schedule. Waiting on Renner for full impacts. 7/29/24 - Slabs have been placed, site drainage piping to be installed this week. The slab details, and finshing have open deffecineis, and will reqiure additional work. 8/12/24 - BV crew is grading for sidewalks and bleacher pads, for a wednesday pour. Renner working on providing pricing for site changes. 8/26/24 - BV / Renner had 20+ people over the weekend site is 95% coplete, one additinal sidewalk pour. Renner notifed that a sidewalk stone needs to be replaced due to ponding. Surfacing paint ing will be starting today. i noted to installer to make sure no middle school layout lies are placed on these courts. 9/9/24 - Approval to occupy was recvived on 9/5/24, and first practice was held on 9/6/24. Renner working on punch list items, and BV has offered additinol sand stone boulders for the large West side of the courts. Once recived Facilites will get equpiment on site for placement. 9/16/24 - Punch is still on going, BVSD has requested updates on the status of the railing with no updates provided by BV or Renner. 9/30/24 - BVSD onsite to relocte boulders. Renner still has punch items to complete and no one was onsite this morning. 10/21/24 - Waiting for final DFPC inspection, Occupency signage brackets are being fabricated. 11/4/24 - Renner working on closeout, and warranty items, caulking still not complete. 11/18/24 - Closeout still ongoing, sealant warranty item still open. 12/2/24 - Renner damaged surfacing while installing the joint sealants. Renner provided movement letter from KWS. 1/6/25 - Renner to perform new survey of the as-build conditions to confirm elevations, BVSD has issued CO for a thrid party to shoot this under a seperate contract. To date renner has yet to provide confirmation. Close out has been delayed due to this issue.
UA Playgrounds (5) Eisenhower, Foothill, Kohl, Louisville ES, Nederland ES | Matt Johnson | 1 | Design Concepts PO 462690 |  | WE O'Neil PO 462828 - Design Phase PO 462967 - Eisenhower ES PO 462968 - Foothill ES PO 462969 - Kohl ES PO 462970 - Louisville ES PO 462971 - Nederland ES | Continental Casualty Company 30213794 Increased Rider 3-11-2024 $2,637,583.29 |  |  |  | 95% |  |  |  |  | 4/10/24 - ASI 01 issued for all locations 5/8/24 - Amendment 2 is complete and all CO's have been processed out to WEO 5/10/24 - WEO to skip SD pricing due to many changes from site walks with Principals 5/20/24 - Tree Removal, BVSD hire the arborost for this or do we perfer to go through WEO 6/3/24 - Foothill & Kohl security fence set, and demo has started. BVSD infomred of late delivery for some equpiment for louisville. 6/17/24 - All locations active, demo ongoing. 7/1/24 - Play equpiment install has started, working through drainage rock issue @ Eisenhower, and elevation slope issues. BVSD ordered ADA swings. Phase II DD pricing received 6/27/24 7/15/24 - All projects active, surfacing has started at Foothill, tree removed. WEO pushed Nedarland due to other needs on on other projects. 7/29/24 - All Site active, final inspections schedlued to take place this week. 8/12/24 - Punch list work taking place at all site, and waiting for WEO to schedlue a back walk inspection. Louisville ES PIP on going currently, WEO confirmed fence will be removed today, asphalt areas cleaned, and safety sweeps. Foothill Es, CPC installed storm drain, and asphalt patching to take place today. 8/26/24 - Punch nearing completion, back walks scheduled for this week. Louiisville punch yet to be schedlued. There are a few swings that need to be adjusted. 9/9/24 - Punch not complete @ Louisville. BVSD still awaiting proposal for correction. WEO working on close out. 9/16/24 - WEO still working on close out, and punch nearing completion. Nederland Panel has been reordered and is roughly 4 weeks out. 9/30/24 - WEO still working on close out, RFI issued for Louisville ES and DCLA replied with confirming additional PIP is warranted. 10/21/24 - WEO provided closeout packages, still working on completion plan for Louisville disc swing. 11/4/24 - Working with DCLA/WEO for plan to correct Louisville, and still working on close out. Currently many missing items, and final accounting still not complete. 11/18/24 - Closeout still ongoing, Louisville swing issue still reviewing options. New leak found @ kohl near spinner. 12/2/24 - BVSD met with WEO for close out, currently all packages are incomplete. 1/6/25 - WEO is still working on the close out package and final numbers quantitfied. To date WEO has issued 3 diffrent packages all of which are not adding up. BVSD & WEO will meet on 1.9.25 to get to a final number for each site.
Boulder High Phase 2 | Christoph Konradi | 2 | Larson Incitti (LIA) PO 462957 |  | JHL PO 460035 |  |  |  | 2025-08-01 |  | 2024-02-08 |  |  |  | 04-15: SD Drawings 04-05. Ned to set up meetings with Maintenence and DAT 05-01: Page Flip for SD was done 04-24 05-01: Coordinating the design schedule LIA modified slipping one month. 05-20: Schedule back in line, JHL has presented their SD estimate, we are over LIA priorities have been discussed. Exterior doors have been walk, sealant walk has been done, LIA has engaged Grimditch. 06-17: Window was done, Option for REnewal of wood windows is beening explored, Ceiling, Walls and floor finish walk is shceudles for june 19th. DD rawings are du July 1st. precon OAC starting after july 1st. 7-01: DD set coming in today. requested priority lists. walked the school for all major scope itmes since SD. some parking only has 3" of asphalt. 7-15: DD page flip was done facility comments are collected and will be sent out. Follow up meeting with JHL LIA this wednesday 7-17-2024, set was shared with principle. need to start cooordiante with security on their door hardware grants. Pricing page filp still coming with consideration of priorities. 8-15: DD budget ~600 k over budget, walked the site with LIA for VE items. abadement coordination has started. 08-26: Abadement Phasing has started, exterior guard rails were taken out of scope, Hail damaged roof was assigned as alternate to get pricing for insurcance purposes. Lackluster graphics package received. GOING FORWARD NOTES WILL BE UNDER THE PHASE 2 TAB.
Arapahoe Ridge Campus | Charles Zachemsky | 2 | Cunningham PO 462896 |  | FCI PO 462741 | [9 empty] | 4/8/24 - FCI/CGA - Have had first 3 DATs. Fire sprinkler sub & abatement consultant have walked school with FCI; determination is that it's not necessary to try to get abatement completed summer '24. Sprinkler design will continue and spot abatement will occur during shorter breaks during school year.
Monarch HS | Charles Zachemsky | 2 | RTA PO 462966 |  | GH Phipps PO 463195 | [9 empty] | 4/8/24 - RTA/GH Phipps - Have had 3 DATs. Going fine.
Monarch K8 | Charles Zachemsky | 2 | RTA PO 463107 |  | GH Phipps PO 463194 | [9 empty] | 4/8/24 - RTA/GH Phipps - Have had 3 DATs. Going fine.
Summit MS | Gene Temanson | 2 | Cuningham PO 463122 |  | Palace Construction PO | [9 empty] | 01-22 Proposal from Cuningham due in January. BVSD will work with Cuningham on documenting the VFA items that have been completed in February.
Escuela Bilingue Pioneer | Stephen Henry | 2 | LOA PO 463136 & PO 463135 |  | Bryan Construction PO | [9 empty] | 3/4/2024 - EVAL Mtg for Architect selection scheduled for 3/5 followed by CMGC on the 14th
Louisville ES | Stephen Henry | 2 | MOA PO 463192 |  | Howell Construction PO 463133 | [9 empty] | 3/4/2024 - Initial walks with MOA completed on 3/1 as well as kickoff Mtg with Howell 4/27/2024 - SD Drawings and Narrative expected the week of 5/3
Louisville MS | Stephen Henry | 2 | MOA PO 463191 |  | Howell Construction PO 463134 | [9 empty] | 3/4/2024 - Initial walks with MOA completed on 3/1 as well as kickoff Mtg with Howell 4/27/2024 - SD Drawings and Narrative expected the week of 5/3
Ryan ES | Stephen Henry | 2 | LOA PO 463142 & PO 463141 |  | Bryan Construction PO | [9 empty] | 3/4/2024 - EVAL Mtg for Architect selection scheduled for 3/5 followed by CMGC on the 14th
Boulder High | Christoph Konradi | 2 | LIA Architects PO 462957 |  | JHL PO 463035 |  |  |  | 2025-08-15 | [5 empty] | 03-08: LIA Architects doing investigation the next 3 weeks. Trying to get focus groups together with Alana. Need to identify CTE. Have met with CTE and Theater, working on SD’s

## Phase 2
5
Project Name | Project Manager | Project Phase | Architect | Architect COI | General Contractor | P&P Bonds on $150K > Contractors Only | General Contractor COI | Forecasted Temp. Occupancy Cert. (TCO) Date | Estimated Completion | Construction Percent Complete | BOE Contract Approval | Schedule | Budget | TCO Real Date | General Updates / Major Issues Concerns | 11 Month Warranty Walk | 23 Month Warranty Walk
Arapahoe Ridge Campus | Charles Zachemsky | 2 | Cuningham PO 462896 |  | FCI PO 462741 | Western Surety #30237588 |  | 08.01.25 | [6 empty] | 9/16 - DD pricing on track. CDs expected mid October. Project is in striking distance with inflation. Trying to coordinate early abatement for night/weekend sprinkler work. 1/6 - On budget & approved by BOE. Abatement walk on 1/6 & FF&E conference on 1/24.
Monarch HS | Charles Zachemsky | 2 | RTA PO 462966 |  | GH Phipps PO 463195 |  |  | 08.01.25 | [6 empty] | 9/16 - DD pricing okay and on track with inflation funding. Pursuing Pivot for field. Sewer line to Red Tail is not going to be feasible. 1/6 - On budget and approved by BOE. FF&E conference on 1/24.
Monarch K8 | Charles Zachemsky | 2 | RTA PO 463107 |  | GH Phipps PO 463194 |  |  | 08.01.25 | [6 empty] | 9/16 - DD pricing okay and on track with inflation funding. 1/6 - On budget and approved by BOE. FF&E conference on 1/24.
Casey MS | Gene Temanson | 2 | Eidos PO 463092 |  | Taylor Kohrs PO 463167 | Western Surety #30238235 |  | 08.01.25 |  | 0 |  |  |  |  | 12.02 - GMP bid pack to BoE meeting on the 10th. 02.10 - Submittals, logistic plans, etc
Horizons K8 | Gene Temanson | 2 | Eidos PO 463102 |  | Taylor Kohrs PO 463220 | Western Surety #30238236 |  | 08.01.25 |  | 0 |  |  |  |  | 11.18 - CD pricing over budget by $423K ($281K after inflation). Currently reviewing the GMP pricing for savings. 12.02 - GMP bid pack to BoE meeting on the 10th. Will require inflation and asbestos funds. 1.6.25 - Permit in process working on 3rd party 4030 submission. Still need to transfer from preieum to cover the cost overage.
Summit MS | Gene Temanson | 2 | Cuningham PO 463122 |  | Palace PO 463221 |  |  | 08.01.25 |  | 0 |  |  |  |  | 12.02 - GMP bid pack to BoE meeting on the 10th. 02.10 - Crews mobilized on 02/03.
BCSIS/HP Additional Heating Coils | Gene Temanson | 2 | Iconergy PO |  | JOC Construction PO 463800 | [9 empty] | 12.02 - Walked with subcontractors last week. No schedule yet on material delivery 02.10 - Crews mobilize tonight. Roughly a 3-4 week duration
BCSIS/HP Lift at Ramp | Gene Temanson | 2 | TBD |  | TBD | [9 empty] | 08.26 -
Louisville ES | Stephen Henry | 2 | MOA PO 463192 |  | Howell PO 463133 | [9 empty] | 01/06/2025 - Base package approved by the board. We are looking at Destratification fans and lighting to possibly add to scope 02/11/2025 - Finalizing Amendment package including Destratification fans and lighting options for pricing today, Howell is anticipating needing 2 weeks or so to finalize their pricing
Louisville MS | Stephen Henry | 2 | MOA PO 463191 |  | Howell PO 463134 | [9 empty] | 01/06/2025 - Board packages are approved including roofing upgrades Looking into adding other possible upgrades including destratification fans and LED Lighting where it does not currentlcy exist. Owner review for additional scope scheduled for 01/16, Challenges with replacing select components of the existing RTU's due to refrigerant changes - we are looking at implications of a full replacement as soon as possible. 02/11/2025 - Submittals are going through for the base scope while also working on finalizing the additional scope we are hoping to add.
Ryan ES | Stephen Henry | 2 | LOA PO 463141 PO 463142 reimburse |  | Bryan PO 463224 | [9 empty] | 01/06/2025 - Base Scope approved through the board. Working on additional scope with Bryan and updated drawings with LOA. 02/11/2025 - DCLA Finalizing additional drawings for landscaping improvements out front along with LOA addressing additional Scope items.
Escuela Bilingue Pioneer | Stephen Henry | 2 | LOA PO 463135 PO 463136 Reimburse |  | Bryan PO 463225 | [9 empty] | 10/21/2024 - Owner review mtg is set for the end of this week 10/25 followed by CD set - should only have minor changes with the exception of the playground scope. 10/29/2024 - Playground scope DD Set anticipated by 11/15 - Pushing on schedule with DCLA as possible to improve. Currently scheduled Bid Set not coming out until 02/05/2025. Balance of scope scheduled for GMP Estimates on 11/8/2024 11/18/2024 - GMP for base scope is expected to come in this week for the December Board meeting. 12/2/2024 - Ongoing scope additions - Base scope is set to go to the board for 12/10/2024 with balance to follow in January - Playground and additional scope added 01/06/2025 - Waiting on updated drawings from DCLA and LOA as well as pricing from Bryan - Bryan seems to be struggling with pricing up these options without full drawinsg. 02/11/2025 -Updated Scope has been identified and DCLA and LOA are finalizing drawings for pricing. Anticipating >800k In additional scope.
EDC Roof Top Units | Stephen Henry | 2 | Eidos PO 462345 |  | MW Golden PO 463974 | [9 empty] | 01/06/2025 - All approvals are complete 01/27/2025 - Pending Submittals from MW Golden 02/11/2025 - Daiken Units are 19 weeks out which puts delivery at the end of June (24th) if the order is finalized today. Submittals are approved as noted with BCER pending JVA structural review.
Boulder High | Christoph Konradi | 2 | LIA Architects PO 462957 HED |  | JHL PO 463203 PO 463035 | Western Surety 30237210 |  |  | 2025-08-15 | [5 empty] | 04-15: SD Drawings 04-05. Ned to set up meetings with Maintenance and DATE 05-01: Page Flip for SD was done 04-24 05-01: Coordinating the design schedule LIA modified slipping one month. 05-20: Schedule back in line, JHL has presented their SD estimate, we are over LIA priorities have been discussed. Exterior doors have been walk, sealant walk has been done, LIA has engaged Grimditch. 06-17: Window was done, Option for Renewal of wood windows is being explored, Ceiling, Walls and floor finish walk is scheduled for june 19th. Drawings are du July 1st. precon OAC starting after july 1st. 7-01: DD set coming in today. requested priority lists. walked the school for all major scope items since SD. some parking only has 3" of asphalt. 7-15: DD page flip was done facility comments are collected and will be sent out. Follow up meeting with JHL LIA this wednesday 7-17-2024, set was shared with principal. need to start coordinate with security on their door hardware grants. Pricing page filp still coming with consideration of priorities. 8-15: DD budget ~600 k over budget, walked the site with LIA for VE items. abadement coordination has started. 08-26: Abatement Phasing has started, exterior guard rails were taken out of scope, Hail damaged roof was assigned as alternate to get pricing for insurance purposes. Lackluster graphics package received. CD's are due 09-20, Owner review 09-27. 09-09: Update on Abatement phasing will be done during Precon OAC 09-10. Requested 3D Axons from LIA. Have provided Record specifications to LIA. 09-16: JHL seems to struggel with schedules related to abatment. Touch base schedule with JHL team 09-17. CD's due 09-23. 09-30: CD's are received, have been submitted to DFPC, Page Flip was done 9-27, Follow up meeting for boilerroom layout, and Guardrail hot spots. 10-21: Phasing discussion is on going, ground/hss have gotten their PO's, RFP is out for Abatement, Furniture RFP is in the works, need to get movers on board for winter work. 11-04: Bid opening from JHL today, Abadment RFP is in progress, HSS, Ground has been borught on board, drawings have been sent to iconergy. 11-18: RFP for furniture all information is in Derells court should be going out very soon, GMP is going to the board 11-19, Walking the AV kitchen system with Principle on thursday, 12-02: Project is in permit review, RFP for furniture is going out soon, Abatment contractor is on board kick off is scheduled for Tuesday 12-03-2024 to discuss abatement over winter break. 01-06-2025: Issues getting my limit updated, permit review is completed. Winter abatement was successful, next step is abatement coordination meetings for spring break and on. RTU's were ordered prior to the 1st.
UA Playgrounds (5) Aspen Creek, Coal Creek, Eldorado, Fireside, & Monarch | Matt Johnson | 2 | Design Concepts PO 462690 |  | FCI PK8 Playgrounds PO #464178 --------------- ES Playgrounds PO #464179 |  |  | 2025-08-01 | [6 empty] | 4/25/24 - SD's recevied 5/2/24 - Onsite Review of SD's 6/5/24 - DD draings recieved, Pricng due back 6/28/24 - Submitted in E-builder for facilites review. 7/1/24 - WEO provided DD pricing for phase 2 8/12/24 - WEO meeting late this week, need to start VE process. 8/26/24 - 75% CD drawings have been completed for Phase II - Estimates show we are tracking on the anticipated budget. 9/9/24 - Need DAT meeting with each school for comments on 75% CD's 9/16/24 - Have met with Coal Creek, Eldorado, Aspen Creek to review current plans. Still trying to get Fireside, Monarch pk-8, and ryan on the schedlue to review the cuurent plans. Still targeting first week of october for 100% CD's 10/21/24 - RFP for contractor selcetion to go out this week. 11/4/24 - RFP still out for contractor selection. 11/18/24 - Contractor selection set for 12.4.24 12/2/24 - DCLA submitted projects for local AHJ review, BVSD paid for these plan reviews. 1/6/25 - Pre-con meeting held with FCI, DCLA, and BVSD. FCI has been provided E-builder log in for the project, and will now attend meetings. All projects are still waiting DFPC review.
Gold Hill Playground | Tom Blahak | 2 | DCLA |  | TBD | [9 empty] | 1/8/25: Master Plans complete, meet with Design Team 1-14. Master Plan 12/20/24 100% DD 1/30/25 Bid Set 3/15/25 Notified Derrell.
Jamestown Playground | Tom Blahak | 2 | DCLA |  | TBD | [9 empty] | 1/8/25: Master Plans complete, meet with Design Team 1-14. Master Plan 12/20/24 100% DD 1/30/25 Bid Set 3/15/25 Notified Derrell.
Nederland MS/HS Turf | Tom Blahak | 2 | N/A |  | TBD | [9 empty] | 1/8/25: RFP 25-20 out on street, inquiries due 1-9, addendum scheduled for 1-16. Bid opening 1-23, proposal review 1-31. 2/4/25: Meeting with Mammoth (new vendor) on 2-5. References are great. 2-10: Mammoth wil perform the work
EDC TI Modifications | Tom Blahak | 2 | Eidos |  | JHL Constructors PO | [9 empty] | 1/28/25: JHL on the job, steel studs and drywall scheduled for week of 2-3. Permit approved, Ground PO issued for 3rd party. Job #971-2201 2/4/25: Job progressing. Having weekly OAC's
Meadowlark Landscaping | Tom Blahak | 2 | N/A |  | CPC | [9 empty] | 1/24/25: Met with CPC and Phil McQuade on site, coming up with plan for CPC to price.

## Phase 3
BOND CONSTRUCTION PROJECTS
Project Name | Project Manager | Project Phase | Architect | Architect COI | General Contractor | P&P Bonds on $150K > Contractors Only | General Contractor COI | Forecasted Temp. Occupancy Cert. (TCO) Date | Estimated Completion | Construction Percent Complete | BOE Contract Approval | Schedule | Budget | TCO Real Date | General Updates / Major Issues Concerns | 11 Month Warranty Walk | 23 Month Warranty Walk
Aspen Creek K8 | Matt Johnson | 3 | BVH Architects PO |  | Alliance PO 463990 | [9 empty] | 9/9/24 - Initial Architect walk held on 9/6, Eidos was the only Architect to show up. Walk to be rescheduled for 2nd attempt 1/6/25 - Troy has provided contacts for generator service, a meeting to walk through this eqiupment will take place in the near future.
BCSIS/High Peaks | Charles Zachemsky | 3 | Eidos PO 464063 |  | Swinerton PO 464137
Birch ES | Stephen Henry | 3 | BVH Architects PO |  | Alliance PO 464029 | [9 empty] | 9/9/2024 - Initial Architect walk held on 9/6, Eidos was the only Architect to show up. 02/11/2025 - First DAT with BVH and Alliance
Centennial MS | Gene Temanson | 3 | Eidos PO 463988 |  | Palace PO 463986 |  |  | 2026-08-01 | 2026-09-01 | [5 empty] | 12.02 - Facility and Eidos walks scheduled for 12.05 02.10 - Facility & bldg reviews occurring. DATs starting
Crest View ES | Gene Temanson | 3 | Eidos PO 463989 |  | Palace PO 463987 |  |  | 2026-08-01 | 2026-09-01 | [5 empty] | 12.02 - Facility and Eidos walks scheduled for 12.05 02.10 - Facility & bldg reviews occurring. DATs starting
Fairview HS (YR1) | Christoph Konradi | 3 | MOA PO 463991 |  | A&P PO 463889 | [9 empty] | 08-05 - Schedule sent to Derrell. Still working on VFA/Scope sheets. 08-21: Architect Walk was Held 08-22: GC Project walk was Held 08-26: Softball scorebaord quote received getting sign off form Harry, Nic approved. 09-16: Addendum for Architect and GC selection has been published. PO for softball scoreboard is out, estimated installed mid October. 10-21: softball score board has been installed, need to get screws installed. MOA and AP were selected as CMGC team. 11-04: Kicks off are scheduled, meeting with principle is scheudled, record drawings are going out this week. 11-18: GC Architecture kick off was on 11-8, we have started Precon OAC's, Principle intro duction and Bond 101 presentations is scheduled for 11-20, Walk with Rob price Scheudled for 11-22, walk with GC Architectu and Facility shceudled for 11-27, Gc will start taking 360 picutres of schools week of the 25th, 12-02: GC has close to 50% of pictures completed, had a good site visit on 11-27-2024, 01-06-2025: We had a pull planning meeting, Architect and AP have meet the facility team and is on a role. site investigating ~%60 done, Site survey was done, Geotech was done, Architect is scheudleing a quick DAT draft to go over the week of january 6th.
Lafayette Bus Terminal | Gene Temanson | 3 | BVH Architects PO |  | Alliance PO 463982 |  |  | 2026-08-01 | 2026-09-01 | [5 empty] | 12.05 - Architect and facility walks tentatively scheduled for mid Dec. 02.10 - Three options drafted and Alliance pricing. Once costs are identified, find funding.
Manhattan MS | Stephen Henry | 3 | Eidos PO 464067 |  | Swinerton PO 464028 | [9 empty] | 9/9/2024 - Inital walks with Architect and CMGC were completed and pending RFP responses 02/11/2024 - Initial DAT was held with the school on 1/29/2025, Eidos and Swinerton.
Mapleton ECC | Gene Temanson | 3 | BVH Architects PO 464066 |  | A.D. Miller PO 464107 |  |  | 2026-08-01 | 2026-09-01 | [5 empty] | 11.18 - AD Miller selected as CMGC; architect TBD. 02.10 - Facility & bldg reviews occurring. Only 2 items on the VFA so DATs will be short.
Platt MS | Charles Zachemsky | 3 | Eidos PO 464046 |  | Swinerton PO 464138
Southern Hills MS | Christoph Konradi | 3 | MOA PO 463992 |  | A&P PO 463898 | [9 empty] | 08-05 - Schedule sent to Derrell. Still working on VFA/Scope sheets. 08-21: Architect Walk was Held 08-22: GC Project walk was Held 09-16: Addendum for Architect and GC selection has been published. 10-21: softball score board has been installed, need to get screws installed. MOA and AP were selected as CMGC team. 11-04: Kicks off are scheduled, meeting with principle is scheudled, record drawings are going out this week. 11-18: GC Architecture kick off was on 11-8, we have started Precon OAC's, Principle intro duction and Bond 101 presentations is scheduled for 11-20, Walk with Rob price Scheudled for 11-22, walk with GC Architectu and Facility shceudled for 11-27, Gc will start taking 360 picutres of schools week of the 25th, 12-02: GC has close to 50% of pictures completed, had a good site visit on 11-27-2024, 01-06-2025: We had a pull planning meeting, Architect and AP have meet the facility team and is on a role. site investigating ~%60 done, Site survey was done, Geotech was done, Architect is scheudleing a quick DAT draft to go over the week of january 6th.
Whittier ES | Gene Temanson | 3 | BVH Architects PO 464067 |  | A.D. Miller PO 464106 |  |  | 2026-08-01 | 2026-09-01 | [5 empty] | 11.18 - AD Miller selected as CMGC; architect TBD. 02.10 - Facility & bldg reviews occurring. DATs starting
UA Playgrounds (5) Bear Creek, Creekside, Eldorado K8, Heatherwood, Mapleton, Mesa ES | Matt Johnson | 3 | Design Concepts PO 462690 |  | FCI PO

## Phase 4
BOND CONSTRUCTION PROJECTS
Project Name | Project Manager | Project Phase | Architect | Architect COI | General Contractor | P&P Bonds on $150K > Contractors Only | General Contractor COI | Forecasted Temp. Occupancy Cert. (TCO) Date | Estimated Completion | Construction Percent Complete | BOE Contract Approval | Schedule | Budget | TCO Real Date | General Updates / Major Issues Concerns | 11 Month Warranty Walk | 23 Month Warranty Walk
Bear Creek ES | Stephen Henry | 4
Coal Creek ES | Charles Zachemsky | 4
Community Montessori | Matt Johnson | 4
Eisenhower ES | PM2 | 4
Eldorado K8 | Gene Temanson | 4
Flatirons ES | Stephen Henry | 4
Foothill ES | Stephen Henry | 4
Gold Hill ES | Gene Temanson | 4
Heatherwood ES | PM2 | 4
Jamestown ES | Gene Temanson | 4
Kohl ES | PM2 | 4
Mesa ES | Stephen Henry | 4
Nederland ES | Gene Temanson | 4
Nederland MS/HS | Gene Temanson | 4
Parkdale / Erie ES | Charles Zachemsky | 4
Superior ES | Gene Temanson | 4
VFA Critical Needs (All Schools) | All PMs

## Fire Alarms
School | VFA budgeted | SD cost est. | SD $ var. | SD % var. | DD cost est. | DD % var. | CD cost est. | CD $ var. | CD % var. | Projections
Broom Heights | 192849 | 821733 | -628884 | 426.1% | 535982 | 277.9% | 566145 | -373296 | 293.6% | 485920 | 100%
Broom High | 375776 | 1827914 | -1452138 | 486.4% | 1017458.337 | 270.8% |  | 375776 | 0% | 1827924.774 | 486.4%
Bear Creek | 39530 |  | 39530 | 0% |  | 0% |  | 39530 | 0% | 140331.5 | 355%
Boulder HS | 300000 |  | 300000 | 0% |  | 0% |  | 300000 | 0% | 1065000
Boulder Prep | 25490 |  | 25490 | 0% |  | 0% |  | 25490 | 0% | 90489.5
Comm. Mont. | 113343 |  | 113343 | 0% |  | 0% |  | 113343 | 0% | 402367.65
Transitions | 13882 |  | 13882 | 0% |  | 0% |  | 13882 | 0% | 49281.1
Eisenhower | 103197 |  | 103197 | 0% |  | 0% |  | 103197 | 0% | 366349.35
Fairview | 497188 |  | 497188 | 0% |  | 0% |  | 497188 | 0% | 1765017.4
Foothill | 333005 |  | 333005 | 0% |  | 0% |  | 333005 | 0% | 1182167.75
Horizons | 90158 |  | 90158 | 0% |  | 0% |  | 90158 | 0% | 320060.9
Kohl | 292896 |  | 292896 | 0% |  | 0% |  | 292896 | 0% | 1039780.8
Louisville MS | 258622 |  | 258622 | 0% |  | 0% |  | 258622 | 0% | 918108.1
Mapleton | 95167 |  | 95167 | 0% |  | 0% |  | 95167 | 0% | 337842.85
MOHI | 458725 |  | 458725 | 0% |  | 0% |  | 458725 | 0% | 1628473.75
MOK8 | 291555 |  | 291555 | 0% |  | 0% |  | 291555 | 0% | 1035020.25
Sanchez | 135525 | 209250 | -73725 | 154.4% |  | 0% |  | 135525 | 0% | 208708.5 | 154%
Southern Hills | 178211 |  | 178211 | 0% |  | 0% |  | 178211 | 0% | 178211
Total | 3795119 | 2858897 | 936222 |  | 1553440.337 |  | 566145 | 3228974 |  | 12555135.17
-8760016.174

## Phase 1
BOND CONSTRUCTION PROJECTS
Project Name | Project Manager | Project Phase | Architect | Architect PO | General Contractor | Contractor PO | Forecasted Temp. Occupancy Cert. (TCO) Date | Estimated Completion | Construction Percent Complete | BOE Contract Approval | Schedule | Budget | TCO Real Date | General Updates / Major Issues Concerns
Alicia Sanchez ES | Stephen Henry | 1 |  | Wold Architects PO# |  |  |  | 2024-08-01
Angevine MS | Tom Blahak | 1 |  | HordCoplanMacht PO# |  |  |  | 2024-08-01 |  | N/A
Boulder Prep | Stephen Henry | 1 |  | BVH Architects PO |  |  |  | 2024-08-01 |  | N/A
Broomfield Heights MS | Charles Zachemsky | 1 |  | TreanorHL PO# |  |  |  | 2024-08-01
Broomfield HS | Charles Zachemsky | 1 |  | TreanorHL PO# |  |  |  | 2025-08-01 |  | 2023-05-09
Centaurus HS | Tom Blahak | 1 |  | HordCoplanMacht PO# |  |  |  | 2024-08-01
Columbine ES | Stephen Henry | 1 |  | BVH Architects PO |  |  |  | 2024-08-01 |  | N/A
Ed Center Rooftop Units | Stephen Henry | 1
Fireside ES | Charles Zachemsky | 1 |  | TreanorHL PO# |  |  |  | 2024-08-01
HVAC Controls | Maint - Travis Cook | 1 |  | ~ |  | Westover 30 - POs
Justice HS | Stephen Henry | 1 |  | Wold Architects PO# |  |  |  | 2024-08-01
Lafayette ES | Stephen Henry | 1 |  | Wold Architects PO# |  |  |  | 2024-08-01
Meadowlark Site Work | Tom Blahak | 1 |  |  |  | CPC Constructors PO# |  | 2023-12-30 |  | 2023-02-28
Modular Factory | Charles Zachemsky | 1
Nederland ES ADA Restrooms | Gene Temanson | 1 |  |  |  | JOC Construction PO#461919 - B |  | 6692520 |  | N/A
New Vista HS | Gene Temanson | 1 |  | MOA PO# |  | A&P PO# |  | 2025-08-01
Roofing Projects (1) Eldo K8 | Stephen Henry | 1 |  | RoofTech |  | Superior Roof PO# | 2023-06-01 | 2023-08-01 | 100% |  |  |  |  | Construction is complete - working through final inspections and remaining punch list items
Roofing Projects (2) Aspen Creek | Stephen Henry | 1 |  | RoofTech |  | Superior Roof PO# | 2023-06-01 | 2023-08-01 | 100%
Roofing Projects (3) Louisville MS | Stephen Henry | 1 |  |  |  |  | 2024-06-01 | 2024-08-01 | 0%
Roofing Projects (4) Lafayette ES | Stephen Henry | 1 |  |  |  |  | 2024-06-01 | 2024-08-01 | 0% |  |  |  |  | Repairs made - August/September 2023
Shade Shelters (1) Meadowlark | Stephen Henry | 1 |  | ~ |  | A to Z Recreation |  | 2023-10-01 | 50% | N/A
Shade Shelters (2) Emerald | Stephen Henry | 1 |  | ~ |  | A to Z Recreation |  | 2023-10-01 | 0% | N/A |  |  |  | Adding walkway from the existing sidewalk to the structure
Shade Shelters (3) Halcyon | Stephen Henry | 1 |  | ~ |  | A to Z Recreation |  | 2023-10-01 | 0% | N/A
Shade Shelters (4) Douglass | Stephen Henry | 1 |  | ~ |  | A to Z Recreation |  | 2023-10-01 | 0% | N/A
Teaching Kitchen | Tom Blahak | 1
University Hills ES | Gene Temanson | 1 |  | BVH Architects PO | [5 empty] | N/A